## RFI Register
AL NAKHEEL TOWER — PACKAGE 3, STRUCTURAL WORKS
REQUEST FOR INFORMATION (RFI) REGISTER ¦ Ref: ANT-RFI-LOG-001 ¦ Updated: 01 April 2026 ¦ Contract Ref: ANRD/PKG3/STRUCT/2025-001
Employer: | Al Nakheel Real Estate Development Co. |  | Engineer: | Al Masaar Engineering Consultants Co. |  | Reference Date: | 01 April 2026 | STATUS KEY:
Contractor: | Gulf Consolidated Contracting WLL |  | RFI SLA: | 14 calendar days from submission |  | Revision: | Rev. A — Initial Issue | CLOSED ¦ OPEN – IN REVIEW ¦ OPEN – OVERDUE ¦ OPEN – PENDING INFO
RFI No. | Date Submitted | Subject | Submitted By | Directed To | Status | Date Answered | Days Open | Remarks / Action Required | Spec / Drawing Ref. | Priority
RFI-001 | 05 Jan 2026 | Foundation Waterproofing Membrane Specification | Site Engineer | Engineer / Structural | CLOSED | 14 Jan 2026 | 9 | Crystalline admixture Type 1 confirmed per ANT-STR-SPEC-001 §5.5.2. Xypex Admix C-2000 approved. Contractor to re-submit method statement. | ANT-STR-SPEC-001 §5.5.2 Dwg ANT-STR-DWG-042 | HIGH
RFI-002 | 12 Jan 2026 | تفاصيل العزل المائي لبئر المصعد (Elevator Pit Waterproofing Detail) | Structural Engineer | Engineer / Architect | CLOSED | 20 Jan 2026 | 8 | Confirmed: 2-coat crystalline membrane to all internal faces + Type 1 admixture to concrete. Waterstop to all construction joints. See revised Dwg ANT-STR-DWG-061 Rev.C. | Dwg ANT-STR-DWG-061 ANT-STR-SPEC-001 §5.5 | HIGH
RFI-003 | 19 Jan 2026 | تسليح قاعدة الجدار القصي (Rebar Lap Splice Length at Shear Wall Base) | Structural Engineer | Engineer / Structural | CLOSED | 30 Jan 2026 | 11 | Class B tension lap = 1,450 mm for T32 bars (Grade 60, ACI 318-19 Table 25.5.2.1). Drawing ANT-STR-DWG-088 to be revised to reflect. RFI closed. | ACI 318-19 §25.5.2 Dwg ANT-STR-DWG-088 | HIGH
RFI-004 | 02 Feb 2026 | Column Base Plate Grout Specification | MEP Coordinator | Engineer / Structural | CLOSED | 13 Feb 2026 | 11 | Non-shrink cementitious grout (Masterflow 928 or approved equiv.), min. compressive strength 50 MPa at 28 days. Placement by pressure grouting through grout holes. Dwg ANT-STR-DWG-104 updated. | Dwg ANT-STR-DWG-104 ASTM C1107 | MEDIUM
RFI-005 | 10 Feb 2026 | توصيل الصلب الإنشائي — مراجعة التفاصيل (Structural Steel Connection Detail Revision — Grid C/7) | Site Engineer | Engineer / Structural | CLOSED | 21 Feb 2026 | 11 | Engineer confirmed revised connection plate thickness 20mm → 25mm. Full-penetration butt weld to replace fillet weld. Revised Dwg ANT-STR-DWG-119 Rev.D issued 21 Feb 2026. | Dwg ANT-STR-DWG-119 BS EN 1993-1-8 | HIGH
RFI-006 | 23 Mar 2026 | MEP Coordination at Level 3 Plant Room — Structural Penetrations | MEP Coordinator | Engineer / MEP + Structural | OPEN — IN REVIEW | — | 9 | Co-ordination clash identified between HVAC duct sleeve and RC transfer beam web at Grid E/3. Await Engineer's instruction on supplementary reinforcement or revised duct routing. Urgent — affects Level 3 slab pour sequence. | Dwg ANT-MEP-DWG-033 Dwg ANT-STR-DWG-178 | HIGH
RFI-007 | 25 Mar 2026 | تفاصيل فاصل التمدد عند واجهة البودیوم (Expansion Joint Details at Podium Interface) | Site Engineer | Engineer / Structural | OPEN — IN REVIEW | — | 7 | Specification calls for 50mm Armaflex-filled expansion joint but Dwg ANT-STR-DWG-155 shows 25mm gap. Contractor requests clarification before podium edge beam shuttering is fixed. Response required within 5 days. | ANT-STR-SPEC-001 §3.6 Dwg ANT-STR-DWG-155 | HIGH
RFI-008 | 27 Mar 2026 | Facade Bracket Spacing Confirmation — North Elevation | Structural Engineer | Engineer / Facade | OPEN — IN REVIEW | — | 5 | Contractor requests confirmation of anchor bracket spacing at 1,200mm vs 1,500mm as shown on two conflicting drawings. Curtain wall sub-contractor cannot proceed with shop drawings until confirmed. | Dwg ANT-FAC-DWG-011 Dwg ANT-FAC-DWG-014 | MEDIUM
RFI-009 | 29 Mar 2026 | تحديد تسلسل صب الخرسانة للبلاطة الانتقالية (Concrete Pour Sequence for Transfer Slab — Level 5) | Contractor QS | Engineer / Structural | OPEN — IN REVIEW | — | 3 | Contractor proposes splitting L5 transfer slab into 4 pours with construction joints at Grid lines 4 and 7. Awaiting Engineer's acceptance of pour sequence and construction joint locations before temporary propping scheme can be finalised. | Dwg ANT-STR-DWG-201 ACI 301-16 §5.3 | HIGH
RFI-010 | 26 Feb 2026 | Curtain Wall Anchor Bolt Embedment Depth — Levels 8–14 | Site Engineer | Engineer / Facade + Structural | OPEN — OVERDUE | — | 34 | ⚠ OVERDUE — SLA EXCEEDED. Contractor awaiting confirmation of embedment depth for M24 anchor bolts cast into perimeter RC columns (Levels 8–14). 14-day SLA expired 12 Mar 2026. Fabrication of curtain wall frames on hold pending response. | Dwg ANT-FAC-DWG-007 Dwg ANT-STR-DWG-142 | CRITICAL
RFI-011 | 01 Mar 2026 | تصنيف مقاومة الحريق لاختراقات المرافق (Fire Rating for Service Penetrations — Floors B1 to L2) | MEP Coordinator | Engineer / MEP + Fire | OPEN — OVERDUE | — | 31 | ⚠ OVERDUE — SLA EXCEEDED. Fire stopping specification required for MEP service penetrations through rated compartment walls and slabs (B1–L2). Specified system contradicts approved fire strategy. 14-day SLA expired 15 Mar 2026. Installation works halted. | ANT-MEP-SPEC-002 §7.4 Dwg ANT-MEP-DWG-018 | CRITICAL
RFI-012 | 05 Mar 2026 | مواصفة الخرسانة لقاعدة خزان الوقود (Generator Fuel Tank Bund Capacity & Concrete Specification) | Contractor QS | Engineer / MEP + Structural | OPEN — OVERDUE | — | 27 | ⚠ OVERDUE — SLA EXCEEDED. RFI requests confirmation of bund capacity (110% tank volume per NFPA 30) and whether bund walls require Grade C40/50 sulphate-resistant concrete. Design drawings do not specify concrete grade for bund. SLA expired 19 Mar 2026. | NFPA 30:2021 §22.11 Dwg ANT-MEP-DWG-044 | HIGH
RFI-013 | 10 Mar 2026 | Temporary Works Loading on Permanent Structure — L4 Reshoring | Structural Engineer | Engineer / Structural | OPEN — OVERDUE | — | 22 | ⚠ OVERDUE — SLA EXCEEDED. Contractor's temporary works designer requires Engineer's written acceptance that the L4 permanent slab (C40/50, 350mm thick, 18 days old) can accept reshoring loads of 28 kN/m² from L5 transfer slab falsework. SLA expired 24 Mar 2026. Programme impact if not resolved by 07 Apr 2026. | BS 5975:2019 Dwg ANT-STR-DWG-201 | CRITICAL
RFI-014 | 15 Mar 2026 | تسلسل تركيب وحدات دورات المياه الجاهزة (Toilet Pod Installation Sequence — Levels 10–18) | Site Engineer | Engineer / Architect + MEP | OPEN — PENDING INFO | — | 17 | PENDING INFO — Awaiting Contractor. Engineer requested Contractor's proposed lifting scheme, pod weight certification, and MEP connection details before approving installation sequence. No response from Contractor since 22 Mar 2026. Contractor to submit within 5 days or RFI will be closed as withdrawn. | Dwg ANT-ARCH-DWG-210 ANT-MEP-SPEC-002 §9 | MEDIUM
RFI-015 | 22 Mar 2026 | Roof Parapet Waterproofing Termination Detail | Contractor QS | Engineer / Architect | OPEN — PENDING INFO | — | 10 | PENDING INFO — Awaiting Contractor. Engineer has requested the Contractor supply the manufacturer's technical data sheet and third-party test certificate for the proposed SBS modified bitumen membrane before approving the termination detail. Contractor's submittal (SD-WAT-018) still outstanding as at 01 Apr 2026. | ANT-ARCH-SPEC-003 §8.2 Dwg ANT-ARCH-DWG-305 | MEDIUM
SUMMARY TOTALS ¦ Total RFIs: 15 |  |  | ✔ CLOSED: 5 |  | ● OPEN — IN REVIEW: 4 |  | ⚠ OPEN — OVERDUE: 4 |  | ◌ PENDING INFO: 2
SLA: 14 calendar days from date of submission. OVERDUE = no response within SLA period. This register is maintained by the Contractor and submitted to the Engineer monthly. Ref: FIDIC Red Book 1999 Sub-Clause 4.1 & Contract RFI Procedure ANT-PM-PROC-003.

## Dashboard
RFI STATUS DASHBOARD — Al Nakheel Tower Package 3
Reference Date: 01 April 2026 ¦ Document: ANT-RFI-LOG-001 Rev. A
METRIC | COUNT | STATUS COLOUR | #
Total RFIs Raised | 15 | —
CLOSED | 5 | GREEN | RFI-001 to RFI-005
OPEN — IN REVIEW | 4 | BLUE | RFI-006 to RFI-009
OPEN — OVERDUE | 4 | RED | RFI-010 to RFI-013
OPEN — PENDING INFO | 2 | PURPLE | RFI-014 to RFI-015
Total Open RFIs | 10 | —
Critical Priority | 3 | — | RFI-010, 011, 013
High Priority | 7 | — | RFI-001,003,006,007,009,012
Average Days Open (all) | 12.1 | —
Max Days Open | 34 | — | RFI-010 (OVERDUE)
SLA Compliance Rate | 67% | — | 5 of 7 answered on time